## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2171-swen-261-10-e CheckChamps
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | JOM
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | JOM
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  | JOM
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | JOM
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | JOM
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | JOM
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  | JOM
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | JOM
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | JOM
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | KDL
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | KDL
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | KDL
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | KDL
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | KDL
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | KDL
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | KDL
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | KDL
As a Player I want to have my piece become a king so that I can move both ways across the board. | Given a piece makes it to the last row (index 7) and isn't already a king when it moves there then it should become a King Piece. | [5 empty] | JMR
As a Player I want to be able to move regular pieces on the board so that I can eventually jump or capture pieces according to the rules of checkers. | Given that it is my turn when I attempt to place a non-king piece on the correctly colored square, non-occupied, adjacent squre then the piece should move to that square. | [5 empty] | JMR
| Given that it is my turn, when I try to move a piece to a nonadjacent square, the wrong colored square, or an occupied square, then the game should not allow it, and make me redo the move. | [5 empty] | JMR
| Given that it is my turn when I try to jump an opponents piece then my piece should go to the correct spot but the jumped piece should not dissappear yet. | [5 empty] | JMR
| Given that a valid jump was submitted when I try to submit another jump then I should be able to. | [5 empty] | JMR
As a Player I want to be able to move King pieces on the board so that I can eventually jump or capture pieces according to the rules of checkers. Code will be very similar to Move Regular Pieces. Possibly just an additional check in the move validation to see if piece is King or Single, and if the former, allow backwards movement. | Given that my piece is a king piece, when I attempt to move the piece like above, then I should be able to also move the piece onto adjacent squares backward along the board. | [5 empty] | JMR
| Given that it is my turn, when I try to move a piece to a nonadjacent square, the wrong colored square, or an occupied square, then the game should not allow it, and make me redo the move. | [5 empty] | JMR
| Given that it is my turn, when I submit a move that is valid, then the board should render correctly for the other player. | [5 empty] | JMR
As a player I want to be able to resign a game, giving the opponent the victory but ending the game. | Given a current-turn player when the off-turn player resigns then the current-turn player should only be kicked to home when they submit the turn. | [5 empty] | CH
| Given an off-turn player when the current-turn player resigns then the off-turn player should be kicked to home when checkTurn triggers. | [5 empty] | CH
| Given either player when the player chooses to resign then they should be immediately removed to Home and talked down on. | [5 empty] | CH
| Given a resigned played when this player returns to the home page then they should be able to start and play other games just like normal. | [5 empty] | CH, found small bug, quickly fixed.
As a Player I want to be able to undo one or more of my moves after I play them so that I can pick a different sequence of moves. | Given a valid, stable turn when I choose to 'Undo Move' then I expect the board to return to the state it was in prior to the most recently placed Move. | [5 empty] | CH
| Given an initial board with no moves when I try to Undo Move then I should not be allowed to undo the move because there are no moves to roll back to. | [5 empty] | CH
| Given a single Move to be undone more than one turn in when Undo Move is called then the program should only be able to undo moves that the current player has placed. | [5 empty] | CH
As a Player I want to be able to jump over one or more of my opponents pieces, so that those pieces get removed from the board. | Given A valid 'jump' move that takes my piece over one or more of my opponents pieces when I initiate the jump then the jumped pieces should be removed from the board, and the current player's turn should continue if more valid jump moves remain. | [5 empty] | JMR
| Given that a valid jump was submitted when I try to submit another jump then I should be able to. | [5 empty] | JMR
| Given that the current player has a capture on the board to be made, when the current player makes the move then the game must ensure the move made was a jump before letting play continue. | [5 empty] | JMR
As a Player I want to be able to end or win the game | Given either player signs out mid-game when the other players game refreshes then the other player should be kicked to the home page nad told they won.
Given a valid game when there are no pieces left on the board then the player with pieces left is declared the winner and both players are kicked back to the home page.
Given a valid game when either player resigns the game then both players should be kicked back to the home page.
As a Player I want to be able to sign in with a persistant account so that my username will stay indefinitely and maybe in the future record stats but not be too pushy cus thats hard. | Given a valid username that doesnt exist and non-empty password when I attempt to sign in with an account then I should be able to sign in normally. | [5 empty] | JMR
| Given a valid username that already exists and the correct password when I enter the information to sign in with an account then I should be able to sign back in to that account. | [5 empty] | JMR
| Given a valid username that already exists and the incorrect password when I enter the information then I should be informed that the password is incorrect. | [5 empty] | JMR
| Given an invalid username when I enter it into the program no matter the password then I should receive an error and be rerouted to the sign-in page again. | [5 empty] | JMR
| Given a query to load the signin with account page when it loads then there should be no error message the first time it loads, unless the previous entry was error-worthy. | [5 empty] | JMR